## Tabelle1
UC Name | Documentation | Frontend | Backend | Warmup Phase | Coding | Testing | Total w/o warmup | Total | Estimate | FP | Explaniation
Register | 0:40 | 0:00 | 0:00 | 2:00 | 2:30 | 0:15 | 3:25 | 5:25 | 3:15 | 37.7 | Gets more time, because of changing Framework
Manage Profile Settings | 0:45 | 0:00 | 0:00 | 0:00 | 2:00 | 0:15 | 3:00 | 3:00 | 2:00 | 29.9 | Gets more time, because of changing Framework
Answer general Information | 0:40 | 0:00 | 0:00 | 0:00 | 2:10 | 0:15 | 3:05 | 3:05 | 3:39 | 42.25 | Gets more time, because of changing Framework
Write Words of cheer | 0:30 | 0:00 | 0:00 | 3:00 | 1:35 | 0:15 | 2:20 | 5:20 | 1:09 | 27.3
Create Guest List | 0:30 | 0:00 | 0:00 | 1:00 | 1:20 | 0:50 | 2:40 | 3:40 | 1:22 | 32.2
Use help function | 0:20 | 0:00 | 0:00 |  |  |  | 0:20 | 0:20 | 2:21 | 27.3
save information | 0:30 | 0:00 | 0:00 |  |  |  | 0:30 | 0:30 | 2:21 | 27.3
Register | Count | Simple | Average | Complex | FTR/RET | DET | Points | Misc | Function points
Number of User Input (Ei) | 5 | 1 | 0 | 0 | 0 | 5 | 15 |  | 37.7
Number of User Outputs (EO) | 2 | 1 | 0 | 0 | 0 | 1 | 8
Number of User Inquiries (EQ) | 7 | 1 | 0 | 0 | 0 | 4 | 21
Number of Files (ILF) | 2 | 1 | 0 | 0 | 1 | 1 | 14 |  |  |  |  | Time spent (w/o outliers) | Function Points (w/o outliers) | Velocity
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 11.8333 | 137.15 | 11.5901
Manage Profile Settings | Count | Simple | Average | Complex | FTR/RET | DET | Points | Misc | Function points
Number of User Input (Ei) | 4 | 1 | 0 | 0 | 2 | 4 | 12 |  | 29.9
Number of User Outputs (EO) | 2 | 1 | 0 | 0 | 0 | 1 | 8
Number of User Inquiries (EQ) | 4 | 1 | 0 | 0 | 0 | 4 | 12
Number of Files (ILF) | 2 | 1 | 0 | 0 | 1 | 1 | 14
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Answer general Information | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 6 | 1 | 0 | 0 | 3 | 4 | 18 | There are 4 user inputs, all form one Database Recor | 42.25
Number of User Outputs (EO) | 3 | 1 | 0 | 0 | 0 | 2 | 12
Number of User Inquiries (EQ) | 7 | 1 | 0 | 0 | 0 | 4 | 21
Number of Files (ILF) | 2 | 1 | 0 | 0 | 1 | 1 | 14 | Presenter, User Model
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Write Words of cheer | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 0 | 0 | 3 | The amount depends on the survey in the database. That makes presenting the survey more comlex | 27.3
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 1 | 0 | 4
Number of User Inquiries (EQ) | 6 | 1 | 0 | 0 | 0 | 2 | 18
Number of Files (ILF) | 2 | 1 | 0 | 0 | 0 | 0 | 14 | Presenter, Bar Model, Question Model
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Create guest list | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 2 | 1 | 0 | 0 | 0 | 2 | 6 | The amount depends on the survey in the database. That makes presenting the survey more comlex | 32.2
Number of User Outputs (EO) | 2 | 1 | 0 | 0 | 0 | 0 | 8
Number of User Inquiries (EQ) | 6 | 1 | 0 | 0 | 0 | 2 | 18
Number of Files (ILF) | 2 | 1 | 0 | 0 | 0 | 0 | 14 | Presenter, Bar Model, Question Model
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Use help function | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 0 | 0 | 3 | The amount depends on the survey in the database. That makes presenting the survey more comlex | 27.3
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 0 | 0 | 4
Number of User Inquiries (EQ) | 6 | 1 | 0 | 0 | 0 | 0 | 18
Number of Files (ILF) | 2 | 1 | 0 | 0 | 0 | 0 | 14 | Presenter, Bar Model, Question Model
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
save information | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 0 | 0 | 3 | The amount depends on the survey in the database. That makes presenting the survey more comlex | 27.3
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 0 | 0 | 4
Number of User Inquiries (EQ) | 6 | 1 | 0 | 0 | 0 | 0 | 18
Number of Files (ILF) | 2 | 1 | 0 | 0 | 0 | 0 | 14 | Presenter, Bar Model, Question Model
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0